The Older People’s Voice – Community Toilet Scheme research brief

Background

The Older People's Voice is a group of older people working together to make B&NES a great place to grow old.  A key issue for many people is the lack of toilets available.

In some other local authority areas, community toilet schemes have been developed where shops, cafes, community buildings etc. have offered their facilities to older people and to demonstrate this they place a sticker in the window.

In order to contribute to addressing this issue

We are seeking a freelancer with good knowledge of B&NES to:

- Research community toilet schemes in other areas to build on their knowledge and experience.

- Approach businesses throughout the area to explain the scheme and seek their support

  - We expect to target 25 organisations / Businesses /Venues business and achieve a successful outcome with at least 6 of them

  - As a result of this work we also want to better understand what will influence further commitments in the future and how that might be achieved

- Develop a database of this information that could be updated annually and made available to members of the public and to propose a realistic plan for maintaining this in the future

- Work with key council officers to ensure the scheme has the support of the Council.

Timescale and proposed milestones

| When | What | Notes | Payment schedule |
| --- | --- | --- | --- |
| Late March 2026 | Recruit / contract freelancer / small org | Agreement will reference this specification and applicant’s application / workplan | 30% on receipt of signed contract & workplan |
| Mid-Late April 2026 by agreement | Interim catch up review with OPV Group representatives |  | 50% on receipt of satisfactory update report and clarification of any questions arising from it |
| Mid – late May 2026 | Present final summary report, recommendations and database. Review / clarification meeting with OPV Group representatives. Then return of docs / data / resources |  | 20% fee |

Fee available

Up to £1500.00 all inclusive. Payable in instalments linked to milestones outlined above. Financial management for his contract will be conducted through AGE UK B&NES

If you are interested:

- Please send a CV and a covering letter  - outlining your interest in, ability to and credentials (inc. use of IT, systems and self-employed status) for undertaking and successfully delivering this work along with an indication of availability during the timeframe outlines above.

- Send by email to Nicola Gregson Chair of the OPV Steering Group at this email address OPVSTEERINGGROUP@GMAIL.COM  by 12 noon on Weds 18th March 2026 or ASAP

- Please also indicate your availability for interview week beginning

Shortlisted applicants will be invited to interview and to propose a workplan with timescales covering the following:

- Proposed methodology for achieving ‘deliverables listed above

- Use of budget in terms of your / staff time and other costs